## Sprint 1
User Story | To Do | In Progress | Impediment | Sprint Backlog | To Verify | Done
1. Auth Module | [5 empty] | Get all Bank names webapi and testing (Rahul)
Get all Card Types webapi and testing (Rahul)
Get IFSC Code by bank Id webapi and testing (Rahul)
Register new user along with card webapi and testing (Rahul)
Implement JWT auth on backend (Rahul)
Login user webapi and testing (Rahul)
Integrate Registration UI in angular (Alok)
Implement Login UI in angular (Alok)
Get Complete User Details webapi and testing (Rahul)
2. Product Module | [5 empty] | All Products webapi and testing (Viraj)
All products angular UI (Viraj)
Product details webapi and testing (Alok)
Product details angular UI (Alok)
All schemes webapi and testing (Alok)
All schemes angular form (Alok)
Check Product Buy possible webapi and testing (Rahul)
Check Product Pay possible webapi and testing (Rahul)
Integrate services in angular UI (Rahul)
3. Dashboard | [5 empty] | Get user details webapi and testing (Shambhavi)
Get debit transactions for a user webapi and testing(Shambhavi)
Get credit transactions for user webapi and testing (Shambhavi)
4. Admin module | [5 empty] | Get all users webapi and testing (Viraj)
Get all cards webapi and testing (Viraj)
Integrate services in angular UI (Alok)
Complete user details by id webapi and testing (Viraj)
Get card details webapi and testing (Viraj)
Update card details webapi and testing (Viraj)

## Sprint 2
User Story | To Do | In Progress | Impediment | Sprint Backlog | To Verify | Done
1. Auth Module | [5 empty] | Reset Password webapi and testing (Shambhavi)
Reset password UI in angular (Shambhavi)
Forget Password webapi and testing (Shambhavi)
Forget Password UI in angular (Shambhavi)
2. Product Module | [5 empty] | Buy Product with auth webapi and testing (Rahul)
Pay product webapi and testing (Rahul)
Get corresponding debit transaction webapi and testing (Rahul)
Integrate services angular UI (Rahul)
3. Dashboard | [5 empty] | Integrate dashboard UI end to end (Shambhavi)
4. Admin module | [5 empty] | Implement all services in angular (Viraj)
Integrate services in Angular UI (Viraj)
5. Static Pages | [5 empty] | About Us (Alok)
Terms and conditions (Alok)
FAQ's in product details (Alok)